## Sheet2
TENDERS / CONTRACTS UNDER INTEGRITY PACT IN COCHIN PORT TRUST AS ON 31.01.2024
Sl. No. | Name of work and location | Estimated Cost (Rs.) in crores | Tendered Cost (Rs.) in crores | % Above/ Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of completion | Name & Address of the Engineer in Charge | Remarks
A. CIVIL ENGINEERING CONTRACTS
1 | Re-construction of North Jetty at Naval Base, Kochi on EPC contract basis. | 461.6 | 399.51 | (-)13.45 | Agt.No.1 of 2021-22 | M/s AFCONS Infrastructure Ltd; Andheri (W), Mumbai-400053 | 22.10.2020 | 48 months. Extended upto 11.01.2025 | EIC Civil: E Rema, Chief Engineer, EIC Electrical: Ajaykumar, EE(Ele) | LOA issued on 22.10.2020. Physical progress 64 % and the work is in progress.
2 | Dredging for maintenance of channels and basins at Cochin Port for the year 2021-22 | 98.64 | 122.5 | (+) 24.19 | Agt.No. 2 of 2021-22 and Suppliment-ary Agreement No.01 & 2 | M/s Dredging Corporation of India Ltd. | 17.05.2021 | 12 months Extended upto 16.05.2023 , further extended upto 16.05.2024 | Siny Mathew SE (Tech.) | Physical progress of 100%. Work completed on 16.05.2022. The contract has been extended for one year and was completed on 16.05.2023. (100% for first year extended contract) Further the contract extended for one more year till 16.05.2024. Physical progress 70.83% and the work is in progress
3 | Construction of International and Domestic Cruise Terminal and other allied facilities at Mormugao Port, Goa through EPC contract. | 79 | 74.11 | (-)6.19 | Agt.No.7 of 2022-23 | M/s RCC-ACC JV, 14-F, Vipul Agora, Gurugram, Hariyana | 31.03.2022 | 18 months. Extended upto 31.12.2023. Further extended upto 29.02.2024 | Sri. T P Thadevus SE(L) | LoA issued on 15.03.2022. Work commenced on 31.03.2022. Physical progress 53.50% and the work is in progress.
4 | Upgradation and modernization of Cochin Fisheries Harbour including providing equipments and Dredging work at Thoppumpady, Kochi | 91.97 | 95.54 | (+)3.89 | Agt.No.8 of 2022-23 | M/s RDS Projects Ltd., Shihab Thangal Road, Panampilly Nagar, Kochi -682 024 |  | 18 months | A.G. Sathyan, Dy.CE | LoA issued on 24.08.2022 (Rs 95, 54, 76,330/- + GST).Preparatory works like barricading, soil Investigation etc completed. Show cause Notice issued to the Contractor on 21/03/2023 for slow progress of work. Thereafter, Pile load tests completed on 29.06.2023. Installation of Batching Plant for the project is in progress. Foundation Stone for the project laid on 11.06.2023 jointly by Sri. Parshottam Rupala, Hon’ble Minister of Fisheries, Animal Husbandry & Dairying; Shri Sarbananda Sonowal Hon’ble Union Minister, MoPSW. Another show cause notice issued on 06/07/2023, as there was no subsequent progress in the works. Contractor has Completed marking of pile points and breaking of hard surfaced area for pile installation. As there was no other progress in works, show cause notice has been issued to the Contractor on 30/08/2023 and reply received on 20/09/2023. As the reply is not satisfactory, action was being taken to terminate the Contract after observing contract condition.In the meantime the contractor has approached High court of Kerala on 16.10.2023 with a writ petition praying that High court may be pleased to direct CoPA to appoint a Third party Concillator as per the contract Agreement and also to keep in abeyance all coercive steps including termination of contract.
On 26.10.2023, after hearing the court dictated that the case is dismissed as not maintainable, reserving the right of contractor for availing any other remedies. Thereafter the Contractor has filed a miscelleneous Application (Arbritation)before the commercial court at Kochi on 28.10.2023 seekin (1) to appoint a concillator (2) not to encash performance guarantee and (3) costs and relief. However the same is not yet listed. Thereafter, the contractor had come up with a proposal and had shown some inclination to start the work. Therefore CoPA conducted a meeting with the EPC Contractor, M/S RDS project Ltd., Kochi on 28.12.2023, as a final attempt to resolve all issues connected with the commencement of the work. During discussions, the contractor has expressed his willingness to undertake the work in right earnest as per the agreement terms and conditions and complete the work in a time bound manner. and also agreed to submit a formal letter in this respect. As such, it is expected that all hurdles shall be sorted out and the project works undertaken, with the present Contractor.Thereafter as agreed in the said meeting , the contractors as per letter dated:01.01.2024, conveyed their willingness to undertake the works as per the terms of the contract agreement with right earnestness, in the benefit of all stakeholders. They also submitted the General layout/general arrangement drawings for review and construction programme, seeking in principle approval to proceed with the detailed design and also expressed their willingness to commence the works such as dredging and pile foundation, within 7 days of issue of approval.
5 | Providing Ro-Ro Facilities for Propylene and other cargo handling at Cochin Port | 10.95 | 10.56 | (-)3.6 | Agt.No.10 of 2022-23 | M/s KVJ Builders and Developers Pvt. Ltd., Edappally, Kochi-682 024 | 31.08.2022 | 8 months Extension granted upto 31.01.2024 | A.G. Sathyan, Dy.CE | LoA issued on 16.08.2022 and site handed over on 31.08.2022. Physical progress 55% and the work is in progress.
6 | Consultancy Services for providing Port led development works and allied facilities with specific emphasis on development of multi modal jetties in eastern or western side of five islands viz. Kavaratti, Agatti, Kadmat, Kalpeni and Minicoy in Lakshadweep | NIL | 452 | NA | Agt. No. 6 of 2022-23 | M/s L & T Infrastructure Engineering Ltd, Chennai | 2022-06-20 | 12 months Extended upto 31.12.2023. Further extended upto 31.05.2024 | Sri. T P Thadevus SE(L) | LoA issued on 11.06.2022. Work commence1 on 20.06.2022 . Physical Progress 92% and the work is in progress.
7 | Providing Consultancy service for preparation of Detailed EIA Study. Providing Project Management Consoultancy including Statutory clearances and O & M Consultancy for the proposed water Aerodromes at various Locations in Lekshadweep Islands, Kochi & other locations in India. | 8 | 6.99 | (- ) 12.625 | - | M/s Feedback Highways OMT Pvt. Ltd., First Floor, Tower East, 77A, Sector 18, IFFCO Road, Gurugram -112015, Haryana | 02.08.2023 | 18 months | Sri. T P Thadevus SE (L) | LoA Issued on 28.07.2023 (Rs.699 lakhs plus GST). Work is in progress. Physical progress 12%
B. MECHANICAL ENGINEERING CONTRACTS
1 | Site Survey, Design, Engineering, Manufacture, Supply, Storage, Civil Work, Erection, Testing and Commissioning of 1.5 MWp Grid Connected Floating Solar PV Project in the backwaters near CoPT's walkway avenue between BOT Junction and Kannangatt bridge at Willingdon Island, Cochin Port , Kerala including Operation and Maintenance of the project for a period of 25 years under RESCO Model (BOT) after Operational Acceptance. | 6.75 |  | NA | [5 empty] | KSERC has furnished approval to issue Re-tender for the installation of 1.5MWP Floating Solar project vide their order dated:25.04.2023 and accordingly tender was issued on 08.05.2023 and opened on 17.07.2023 and only single bidder has responded but has not met the MQC and hence the Tender was discharged. A petition has been filed before KSERC on 25.09.2023 for reviewing the Capacity Utilization Factor from 28% to 21% so as to issue retender. In reply KSERC vide letter dated:04.01.2024 has allowed CoPA to modify the CUF as not lower than 21% instead of 28%. Tender wil be issued after approval of competent authority.
C. Marine Contracts
1 | Supply, manning, operation and maintenance of one No. Pilot Launch with steel hull on hire basis to CoPT for 5 years extendable by 2 years. | 8.08 | 6.67 | (-) 17.44 | CME’s Agt. No. 03 of 2016-17 dated: 23.10.2016 | M/s Eastern Navigation Pvt. Ltd; Kolkata-1. | 05.06.2017 | 04.06.2024 | Sri. Rajesh Velayudhan, Chief Engineer (Marine) | Physical progress of 95.07% achieved and service rendered as and when required.
2 | Upgradation of VTMS including warranty period and AMC. | 12.31 | 5.59 | (-)54.59 | DC-1/VTMS/ 2019-20 Dated: 01.02.2020 | M/s Wartsila Voyage Ltd; Dublin, Ireland | 18.01.2020 | 15.09.2021 (installa-tion and commission- ing) 15.09.2022 (warranty period) 15.09.2027 to (AMC period) | Dy. Conservator | Installation & commissioning physical progress 100 %. One year Warranty period commenced on 16.09.2021. After completion of warranty period , 5 year AMC will start. Physical progress 39.51 % and work is in progress.

## Sheet3
TENDERS / CONTRACTS UNDER INTEGRITY PACT IN COCHIN PORT TRUST AS ON 31.07.2023
Sl. No. | Name of work and location | Estimated Cost (Rs.) in crores | Tendered Cost (Rs.) in crores | % Above/ Below Schedule of Rates | Agreement No. | Agency | Date of commencement of work | Time of completion | Name & Address of the Engineer in Charge | Remarks
A. CIVIL ENGINEERING CONTRACTS
1 | Re-construction of North Jetty at Naval Base, Kochi on EPC contract basis. | 461.6 | 399.51 | (-)13.45 | Agt.No.1 of 2021-22 | M/s AFCONS Infrastructure Ltd; Andheri (W), Mumbai-400053 | 22.10.2020 | 48 months. Extended upto 11.01.2025 | EIC Civil: E Rema, Chief Engineer, EIC Electrical: Ajaykumar, EE(Ele) | LOA issued on 22.10.2020. Physical progress 50 % and the work is in progress.
2 | Dredging for maintenance of channels and basins at Cochin Port for the year 2021-22 | 98.64 | 122.5 | (+) 24.19 | Agt.No. 2 of 2021-22 and Suppliment-ary Agreement No.01 & 2 | M/s Dredging Corporation of India Ltd. | 17.05.2021 | 12 months Extended upto 16.05.2023 , further extended upto 16.05.2024 | Siny Mathew SE (Tech.) | Physical progress of 100%. Work completed on 16.05.2022. The contract has been extended for one year and was completed on 16.05.2023. (100% for first year extended contract) Further the contract extended for one more year till 16.05.2024. 20.83% and the work is in progress
3 | Capital Dredging for MULT Jetty Basin at Puthuvypeen in Cochin Port | 70.57 | 65.63 | (-)7 | Agt.No.13 of 2021-22 | M/s Rock & Reef Dredging Pvt. Ltd., Navi Mumbai | 04.03.2022 | 6 months. Extended upto 15.04.2023 in 6 spells | Siny Mathew SE (Tech.) | Work completed on 15.04.2023. Final bill under process. Physical progress 100%
4 | Construction of International and Domestic Cruise Terminal and other allied facilities at Mormugao Port, Goa through EPC contract. | 79 | 74.11 | (-)6.19 | Agt.No.7 of 2022-23 | M/s RCC-ACC JV, 14-F, Vipul Agora, Gurugram, Hariyana | 31.03.2022 | 18 months | Joji Paul, Dy.CE-II | LoA issued on 15.03.2022. Work commenced on 31.03.2022. Physical progress 41% and the work is in progress. Scheduled date of completion 30.09.2023
5 | Upgradation and modernization of Cochin Fisheries Harbour including providing equipments and Dredging work at Thoppumpady, Kochi | 91.97 | 95.54 | (+)3.89 | Agt.No.8 of 2022-23 | M/s RDS Projects Ltd., Shihab Thangal Road, Panampilly Nagar, Kochi -682 024 |  | 18 months | A.G.Sathyan, SE(M) | LoA issued on 24.08.2022. Preparatory works like barricading , soil investigation etc. completed. A Show cause notice issued to the contractor for slow progress of work. Thereafter, pile load tests completed on 29.06.2023. Installation of Batching plant for the project is in progress. Foundation stone for the project laid on 11.06.2023 jointly by Sri.Parshottam Rupala, Hon'ble Minister of Fisheries, Animal Husbandry & Dairying. Shri.Sarbananda Sonowal, Hon'ble Union Minister, MoPSW (through Video conference) Physical progress 0.5%
6 | Providing Ro-Ro Facilities for Propylene and other cargo handling at Cochin Port | 10.95 | 10.56 | (-)3.6 | Agt.No.10 of 2022-23 | M/s KVJ Builders and Developers Pvt. Ltd., Edappally, Kochi-682 024 | 31.08.2022 | 8 months | A.G.Sathyan, SE(M) | LoA issued on 16.08.2022 and site handed over on 31.08.2022. Physical progress 38% and the work is in progress.
7 | Consultancy Services for providing Port led development works and allied facilities with specific emphasis on development of multi modal jetties in eastern or western side of five islands viz. Kavaratti, Agatti, Kadmat, Kalpeni and Minicoy in Lakshadweep | NIL | 452 | NA | Agt. No. 6 of 2022-23 | M/s L & T Infrastructure Engineering Ltd, Chennai | 2022-06-20 | 12 months Extended upto 19.10.2023 | Sri. T P Thadevus EE (CM-II) | LoA issued on 11.06.2022. Work commenced on 20.06.2022 . Physical Progress 88% and the work is in progress.
B. MECHANICAL ENGINEERING CONTRACTS
1 | Site Survey, Design, Engineering, Manufacture, Supply, Storage, Civil Work, Erection, Testing and Commissioning of 1.5 MWp Grid Connected Floating Solar PV Project in the backwaters near CoPT's walkway avenue between BOT Junction and Kannangatt bridge at Willingdon Island, Cochin Port Trust, Kerala including Operation and Maintenance of the project for a period of 25 years under RESCO Model (BOT) after Operational Acceptance. | 6.75 | RESCO model Levelised Tarif Rs. 3.89 per unit. | NA | No. 06 of 2020-21 (PPA) Dtd: 10.01.2021 | M/s Suryam International Pvt. Ltd; Odisha | Power purchase agreement was executed on 10.01.2021 | 12 months after the date of PPA | SE (Ele) | The LoA has been issued on 11.12.2020 with a levelised tariff of Rs.3.89 per unit for 25 years. Power purchase agreement executed on 10.01.2020. Work is expected to be completed within 12 months from the date of execution of PPA. KSERC personal hearing held on 09.03.2022 for the approval of 1.5 MWp Solar project. The commission has rejected the petition filed by Cochin Port Authority for purchase of 1.5 MWp Solar Power from the proposed 1.5MWp solar Power Project under RESCO model at a levelised tariff of Rs.3.89 per KWH vide their order dated: 25.03.2022. Accordingly the contract placed on M/s Suryam International Pvt. Ltd Odisha has been cancelled and terminated the Power Purchase Agreement on 23.05.2022. As per the Competent Authority’s approval, the draft tender document and PPA has been sent to KSERC through a petition dtd:09.12.2022 for approval of Tariff. KSERC conducted personal hearing on 22.02.2023 and directed CoPA to clarify whether there is any deviation to SECI’s guidelines/Standard bidding document of MoP. Submitted revised bid document and PPA on 27.02.2023 and further clarifications as directed by KSERC on 20.03.2023. KSERC has furnished approval to issue re-tender for the installation of 1.5MWP floating Solar project vide their order dated 25.04.2023. Tender issued on 08.05.2023 and opened on 17.07.2023 and only single bidder has quoted who has not submitted the documents to meet MQC and hence the Tender will be discharged and it is proposed to send a letter to KSERC for reducing the Capacity Utilization Factor from 28% to 21% and other modifications for their approval so as to issue re-tender.
C. Marine Contracts
1 | Supply, manning, operation and maintenance of one No. Pilot Launch with steel hull on hire basis to CoPT for 5 years extendable by 2 years. | 8.08 | 6.67 | (-) 17.44 | CME’s Agt. No. 03 of 2016-17 dated: 23.10.2016 | M/s Eastern Navigation Pvt. Ltd; Kolkata-1. | 05.06.2017 | 04.06.2024 | Sri. Rajesh Velayudhan, Chief Engineer (Marine) | Physical progress of 87.93% achieved and service rendered as and when required.
2 | Upgradation of VTMS including warranty period and AMC. | 12.31 | 5.59 | (-)54.59 | DC-1/VTMS/ 2019-20 Dated: 01.02.2020 | M/s Wartsila Voyage Ltd; Dublin, Ireland | 18.01.2020 | 15.09.2021 (installation and commission- ing) 15.09.2022 (warranty period) 15.09.2027 to (AMC period) | Dy. Conservator | Installation & commissioning physical progress 100 %. One year Warranty period commenced on 16.09.2021. After completion of warranty period , 5 year AMC will start. 31.17% in progress.